## Project schedule
| Drone Imagery Parking Management System |  |  |  |  | Project start: | [7 empty] | 2025-09-25
| Members: |  |  |  |  | Display week: | [7 empty] | 2
Lance Van, Bryan Gatto, Khalid Abdallah, Oliver Si, Gabriel Fusaro
[6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17
| TASK | ASSIGNED TO | START | END | time axis 2025-09-29 to 2025-11-23
 | time axis 2025-09-29 to 2025-11-23
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
1st Semester
| Define goals | Team | 2025-09-25 | 2025-10-12 | 18 | bar: 2025-09-29 to 2025-10-12
| Conduct studies | Team | 2025-10-12 | 2025-11-26 | 46
| Set up future meetings | Lance Van | 2025-10-01 | 2025-10-02 | 2
| Define scope | Team | 2025-10-02 | 2025-10-06 | 5
| Prepare for first demo | Team | 2025-11-14 | 2025-12-01 | 18
Implement Subsystems
| Implement Drone flight | Bryan Gatto, Gabriel Fusaro | 2025-11-15 | 2026-01-23 | 70
| Implement Computer Vision | Lance Van | 2025-11-17 | 2026-02-06 | 82
| Implement Cloud system | Oliver Si | 2025-11-17 | 2026-02-13 | 89
| Implement Mobile App | Khalid Abdallah | 2025-11-17 | 2026-02-17 | 93
| Combine All subsystems | Team | 2026-02-17 | 2026-03-01 | 13
Project Management
| Hold weekly team meetings | Team | 2025-10-01 | 2026-05-01 | 213
| Monitor progress | Team | 2025-10-01 | 2026-04-20 | 202
| Manage resources | Team | 2025-10-06 | 2026-04-10 | 187
| Provide updates / Progress reports | Team | 2025-10-01 | 2026-04-20 | 202
| Testing and validation | Tean | 2026-02-13 | 2026-02-23 | 11
2nd Semester
| Prepare Project Poster | Tean | 2026-03-20 | 2026-04-05 | 17
| Prepare final video | Team | 2026-03-25 | 2026-04-10 | 17
| Finalize documentation and code package |  | 2026-04-11 | 2026-04-14 | 4
| Senior Showcase | Team | 2026-04-20 | 2026-04-29 | 10
| Submit final project | Team | 2026-04-29 | 2026-05-07 | 9

## BoM
8 |  |  |  | 2026s ENG4952 Senior Engineering Design Team requsition sheets
Drone Imagery Parking Management System |  |  |  | Grade: A = Worthy of Shark Tank When meeting with Perry, have a short presentation emailed in advance.
|  |  |  | When done put "ready" in b21 | [5 empty] | This is an exam. Points Deducted for items: not filled in -1 or can be found cheaper= -5, items not received in a resonable time= -2.
Students: | Fill in the Blue areas |  |  | Items maybe requested in the first 30days of class. | [15 empty] | Everything after the ? is tracking information -- REMOVE IT.
Professors: | Fill in the Green |  |  | FAU can NOT reimburse you for items you purchase on your own. | [15 empty] | Most websites that use tracking separated with the ? Amazon after the /ref=
Procurement: | All others as needed |  |  | All items designated as "Return to FAU" must be returned upon completion of your project. | [15 empty] | REMOVE everything INCLUDING the =
|  |  |  | This is your complete budget sheet do not delete prior delivered items. List all parts. | [15 empty] | Verify that the link still works.
Total Funds Available | 200 | Availble | 0 | Remove the tracking info from all links. | [8 empty] | Vendor Preference: | Freight | [5 empty] | This means the items including the "/ref="
Lab Fee per Student | 30 | Budget | 200 | see: Labmain for instructions | [8 empty] | Amazon.com | free via Prime | [5 empty] | Do not use shortened URLs. tiny & bitly ...
Total Lab Fees | 150 | Total | 200 | If it is blue, you fill it up with data. | [8 empty] | Newark.com | free | [5 empty] | See examples in i17 vs i18
Team Number | 28 |  |  | Except, blank product lines. | [8 empty] | Digikey.com | Not Free!
Project Name | Drone Imagery Parking Management System | [11 empty] | Grainger.com / McMaster.com | Not Free!
Team Member Names: | Email |  |  | Instructions: |  |  | https://docs.google.com/document/d/19ndtxmOEiLcHj8Pf7w-PEnRkLOI6drgPEd5QUzhhn0Y/edit?tab=t.0 | [5 empty] | MPJA.com | Not Free!
Khalid Abdallah | kabdallah2022@fau.edu |  | 30 | Chat w Perry: |  |  | https://docs.google.com/spreadsheets/d/195xr72tPXvjpT2Or8KzCVWsK5MENJ-U9uzdGPMKf4nI/edit?gid=2145016025#gid=2145016025 | [5 empty] | Arrow.com | Not Free!
Gabriel Fusaro | gfusaro2022@fau.edu |  | 30 | [9 empty] | Mouser.com | Not Free!
Bryan Gatto | bgatto2024@fau.edu |  | 30 | Instructions |  |  | https://docs.google.com/document/d/19ndtxmOEiLcHj8Pf7w-PEnRkLOI6drgPEd5QUzhhn0Y/edit?usp=sharing
Oliver Si | wsi2023@fau.edu |  | 30 | Bad |  |  | https://www.amazon.com/Adafruit-Electret-Microphone-Amplifier-Adjustable/dp/B00K9M6S1O/ref=sr_1_5?ie=UTF8&qid=1510525236&sr=8-5&keywords=arduino+sound+sensor
Lance Van | lvan2019@fau.edu |  | 30 | Good |  |  | https://www.amazon.com/Adafruit-Electret-Microphone-Amplifier-Adjustable/dp/B00K9M6S1O
Complete the following tasks by the End of Semester:
Ready? | ready | When done put "ready" in b21 | [6 empty] | Items Returned? |  |  |  | Full Documentation Emailed to Perry at cweinthal2014@fau.edu? |  |  |  | AWS & OTK Billable Turned off?
[9 empty] | No |  |  |  | No |  |  |  | No
Power Budget starts on line | 60
[5 empty] | Team | 28 |  |  |  | quanity |  |  | Drone Imagery Parking Management System |  |  | 0 | 200 | 0 | 200
|  |  |  | Return to FAU | Grade | Ordered | Here | Received | Expected Arrival DATE or Received | FAU | Team | Loan | Description | $each | $frt / shipping (no = 0) | $tot FAU | $tot Team | $tot Loaned | $tot Project | Sort by Vendor Website Link. Sanitize your links. Remove after the ?
EDIT ROW FOR GROUP PROJECT → clear A column |  |  |  | n |  | y | y | y | 2days |  | 1 |  | Drone | 200 | 0 |  | 200 |  | 200 | https://www.amazon.com/dp/B0FCD63NMH?
EDIT ROW FOR GROUP PROJECT → clear A column
EDIT ROW FOR GROUP PROJECT → clear A column
EDIT ROW FOR GROUP PROJECT → clear A column
0
Power Budget
Watts | Volts | Amps | Hours